## Requirements_Catalog
ROUTINES MVP - TIIMO IPHONE CHURN REDUCTION : REQUIREMENTS CATALOG
| Project ID | Project Manager | Date Initiated
| TIIMO-001 | CHITRANGI | 2026-01-15
| Project Name | Catalog Owner | Date last updated
| ROUTINES MVP CHURN REDUCTION | CHITRANGI | 2026-03-13
REQUIREMENT | [5 empty] | PEOPLE |  |  | RELATED |  | STATUS |  | PRIORITIZATION & METRICS
ID | NAME | DESC | TYPE | PRIORITY | ACCEPTANCE CRITERIA | OWNER | AUTHOR | STAKEHOLDERS | REQUIREMENTS | DOCS | RESOLUTION | VERSION | REACH | IMPACT (1-10) | CONFIDENCE (0-1) | EFFORT | RICE SCORE
FR-01 | Routine Creation | Users create routine w/ 5+ subtasks durations | Functional | Should | Add 5 subtasks w/durations, Save validate | Product | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, Design Lead, Design Team, QA/ Testing Team, Support Team | SR-01 | BPMN file | Proposed | 1 | 10 | 10 | 0.9 | 1.5 | 60
FR-02 | Visual Timer | Visual countdown per subtask auto-advance | Functional | Must | Timer shows remaining time left in suubtakss, 80% completion rate | Dev Lead | BA | Neurodivergent Users, Product Managers, Development Lead, Development Team, Design Lead, Design Team, QA/ Testing Team, Support Team | SR-01 NFR-02 |  | Proposed | 1 | 10 | 10 | 0.9 | 1.5 | 60
NFR-03 | 99% Crash-Free | 99% reliability no crashes during expansion timer | Non-Functional | Must | OOM <1%, Repeat stable | Dev Lead, Q/A Testing Team | BA | Neurodivergent Users, Product Managers, Development Lead, Development Team, QA/ Testing Team, Support Team, Review Platforms | FR-04 FR-06 | VOC crash cluster | Proposed | 1 | 10 | 10 | 0.9 | 1.5 | 60
SR-06 | Product Roadmap | Product needs Routines fit post-AI, more than $75k ROI | Stakeholder | Must | Post-AI roadmap slot, ARR threshold met | Product Manager | Product Manager | Product Managers, Executive Management, Development Lead, Design Lead |  | Roadmap matrix file | Approved | 1 | 9 | 8 | 0.8 | 1 | 57.6
NFR-04 | WCAG AA Accessible | Timers colors high-contrast neuroinclusive, WCAG AA compliant | Non-Functional | Should | AA compliant, Time-blind friendly | Design Lead | BA | Neurodivergent Users, Product Managers, Design Lead, Design Team, QA/ Testing Team, Apple App Store Team | FR-02 | Kano Delight | Proposed | 1 | 9 | 8 | 0.8 | 1 | 57.6
NFR-01 | Routine Creation Time | Complete routine (5 subtasks) creation in less than 2min end-to-end. | Non-Functional | Must | Routine (5 subtasks) creation less than 2min average, less than 3min in 95th percetile during benchmark testing | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, QA/ Testing Team | FR-01 | BPMN To-Be | Proposed | 1 | 10 | 9 | 0.9 | 1.5 | 54
TR-02 | Onboarding Video | 3-min video tutorial for routine setup flow | Transition | Must | ADHD-friendly paced, 80% completion rate | Design Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Design Lead, Design Team, Support Team, Influencers, Review Platforms |  | Design SR-03 | Proposed | 1 | 8 | 8 | 0.8 | 1 | 51.2
FR-03 | Save Deploy Library | Save routine library one-tap deploy to day | Functional | Must | Library persistent, Deploy server deltas | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, Support Team | FR-04 | BPMN To-Be | Proposed | 1 | 9 | 9 | 0.9 | 1.5 | 48.6
NFR-02 | Screen Load Performance | Screens load in less than 2s (95th percentile). | Non-Functional | Must | Routine screens load in less than 2s in 95th percentile, no timeouts. | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, QA/ Testing Team | FR-01 | BPMN To-Be | Proposed | 1 | 10 | 9 | 0.8 | 1.5 | 48
TR-01 | Routines User FAQ | Publish FAQ explaining Routines vs Plans + common issues. | Transition | Could | faq's in the app and website, train support team | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, Support Team |  |  | Proposed | 1 | 5 | 6 | 0.7 | 0.5 | 42
SR-04 | Dev Timer Refactor | Dev needs reusable timer engine for 4 sprint feasibility | Stakeholder | Must | Reuse existing timer, No new crashes | Dev Lead | Development Lead | Development Lead, Development Team, QA/ Testing Team, Product Managers | FR-02 NFR-02 | Tech spike file | Proposed | 1 | 8 | 9 | 0.8 | 1.5 | 38.4
SR-01 | ADHD Timed Flow | ADHD users need reusable routines w/ timed subtasks for time-blind flow | Stakeholder | Must | Visual countdown per subtask, Timer Auto-advance, 80% routine completion rate | Product Manager | Neurodivergent Users | Neurodivergent Users, Product Managers, Development Lead, Design Lead, QA/ Testing Team | FR-01 FR-02 |  | Proposed | 1 | 10 | 10 | 0.9 | 2.5 | 36
SR-05 | Design Tradeoffs | Design needs 5-subtask max simplified flows | Stakeholder | Should | Max 5 subtasks, Visual hierarchy | Design Lead | Design Lead | Design Lead, Design Team, Neurodivergent Users, Product Managers | FR-01 | Persona updates file | Proposed | 1 | 7 | 7 | 0.7 | 1 | 34.3
SR-03 | NeuroInclusive Design Integration | Design needs neuroinclusive UX integration without clutter | Stakeholder | Must | Simplified nav, AI suggest routines | Design Lead | Design Lead | Design Lead, Design Team, Neurodivergent Users, Product Managers | NFR-01 NFR-03 | Wireframes files | Proposed | 1 | 9 | 9 | 0.8 | 2 | 32.4
FR-04 | Server Expansion | Server-side repeat expansion for routines without client crashes | Functional | Must | Nightly batch 14 days, Deltas to clients | Dev Lead | BA | Development Lead, Development Team, QA/ Testing Team, Product Managers, Data Analytics Team, Apple App Store Team | FR-03 FR-06 | BPMN To-Be | Proposed | 1 | 9 | 9 | 0.8 | 2 | 32.4
FR-06 | Batch Add Routine Tasks | Batch add routine tasks without crash during repeats | Functional | Should | Bulk insert safe, Progress indicator | Dev Lead | BA | Neurodivergent Users, Product Managers, Development Lead, Development Team, QA/ Testing Team, Support Team | FR-04 |  | Proposed | 1 | 9 | 9 | 0.75 | 2 | 30.375
BR-01 | Churn Reduction ARR | Reduce iPhone churn 20% via Routines MVP | Business | Must | Adoption >70, Rating >4.5, ARR scenario met | Executive | Product Manager | Product Managers, Executive Management |  | Assumptions-Limitations-Log : ROI scenarios | Approved | 1 | 10 | 10 | 0.9 | 3 | 30
FR-07 | Conflict Check | Check overlaps conflicts before routine deploy | Functional | Could | Visual warnings, Auto-resolve simple | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, Design Lead, Design Team, Q/A / Testing Team | FR-05 |  | Proposed | 1 | 7 | 6 | 0.7 | 1 | 29.4
FR-05 | Calendar Sync | Bi-directional sync routines to external calendars | Functional | Should | Import conflicts resolve, Retain imports | Dev Lead | BA | Neurodivergent Users, Regular Users, Product Managers, Development Lead, Development Team, QA Testing Team, Support Team | FR-07 | VOC calendar complaints | Proposed | 1 | 9 | 8 | 0.8 | 2 | 28.8
SR-07 | Exec Budget | Execs need Q1 $50k budget for MVP | Stakeholder | Should | Dev, Design, QA, resources, Phase 2 approved | Executive Management | Executive Management | Executive Management, Product Managers |  | Budget approval file | Proposed | 1 | 6 | 8 | 0.7 | 1.5 | 22.4
SR-08 | Analytics Alignment | Analytics needs 85% VOC-internal churn match | Stakeholder | Should | Cohort data vs VOC 22% | Data Analytics Team | Data Analytics Team | Data Analytics Team, Product Managers, Executive Management |  | Churn correlation file | Proposed | 1 | 7 | 9 | 0.7 | 2 | 22.05
BR-02 | Adoption KPI | Achieve 70% Routines adoption, rating >4.5 post-MVP | Business | Must | Routines usage 70%, App rating uplift 0.5 pts | Product Manager | Product Manager | Product Managers, Data Analytics Team |  | Elicitation Results Log | Proposed | 1 | 10 | 10 | 0.8 | 4 | 20
SR-02 | MVP Delivery | Product needs Routines MVP delivered in 4 sprints | Stakeholder | Should | Sprint 1: Core create, Sprint 4: Calendar deploy | Product Manager | Product Manager | Product Managers, Development Lead, Development Team, Design Lead, Design Team, QA/ Testing Team | FR-01 to FR-07 |  | Proposed | 1 | 8 | 9 | 0.8 | 4 | 14.4