## Overview
Tiimo Routines MVP Implementation Plan
Objective |  | Business target |  | Delivery window | Governance
Restore a high-value routines capability through a controlled 8-week MVP delivery and a 4-week monitoring period. |  | Support the case study target of reducing iPhone churn by 13 percent and protecting projected ARR. |  | Implementation covers weeks 1-8, followed by weeks 9-12 for KPI monitoring and VOC review. | Two sprint gates plus go-live approval demonstrate disciplined delivery approach.
Phase | Outcome | Timing | Workbook Guide
Sprint 1 | Design and initial development of the MVP completed | Weeks 1-2 | 1. Executive Gantt
Sprint 2 | Server Side logic and integration scope completed | Weeks 3-4 | 2. Delivery Plan
Sprint 3 | QA testing and beta readiness reviewed through UAT and defect triage | Weeks 5-6
Sprint 4 | Release readiness approved and production deployment completed | Weeks 7-8
Monitoring | Adoption, rating, churn, and VOC signals reviewed | Weeks 9-12

## Executive Gantt
Executive Gantt View
Phase | Owner | Start | End | Duration | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
[5 empty] | 01-Apr | 2026-04-08 | 15-Apr | 22-Apr | 29-Apr | 06-May | 13-May | 20-May | 27-May | 03-Jun | 10-Jun | 17-Jun
Sprint 1 validation and delivery | BA / Design / Development / QA | 2026-04-01 | 2026-04-14 | 14 | bar: 01-Apr to 2026-04-08
Sprint 2 validation and delivery | BA / Design / Development / QA | 2026-04-15 | 2026-04-28 | 14 | bar: 15-Apr to 22-Apr
Sprint 3 testing, beta preparation and build | BA / Design / Development / QA | 2026-04-29 | 2026-05-12 | 14 | bar: 29-Apr to 06-May
Sprint 4 release readiness and deployment | BA / Design / Development / QA | 2026-05-13 | 2026-05-22 | 10 | bar: 13-May to 20-May
Post-launch monitoring | BA | 2026-05-25 | 2026-06-19 | 26 | bar: 20-May to 17-Jun
Decision gates |  |  |  |  | 2026-04-08: G1; 06-May: G2; 20-May: Go-live

## Delivery Plan
Detailed Delivery Plan
Task ID | Workstream | Task Name | Owner | Start Date | End Date | Duration (days) | Dependency | Status
PLN-01 | Planning | Project kickoff and sprint planning | PM | 2026-04-01 | 2026-04-02 | 2 |  | Completed
BA-01 | Analysis | Validate Sprint 1 requirements and MVP design | BA | 2026-04-01 | 2026-04-07 | 7 | PLN-01 | Completed
DEV-01 | Build | Develop routine creation and timer capability | Development | 2026-04-08 | 2026-04-14 | 7 | BA-01 | Planned
QA-01 | Quality | Execute Sprint 1 unit testing | QA | 2026-04-13 | 2026-04-14 | 2 | DEV-01 | Planned
G-01 | Governance | Gate 1 approval for Sprint 1 scope | PM | 2026-04-14 | 2026-04-14 | 1 | QA-01 | Planned
BA-02 | Analysis | Refine backlog and validate Sprint 2 process design | BA | 2026-04-15 | 2026-04-18 | 4 | G-01 | Planned
DEV-02 | Build | Develop library save and server-side repeat logic | Development | 2026-04-19 | 2026-04-28 | 10 | BA-02 | Planned
QA-02 | Quality | Execute Sprint 2 integration testing | QA | 2026-04-27 | 2026-04-28 | 2 | DEV-02 | Planned
BA-03 | Analysis | Prepare UAT scenarios using validated personas | BA | 2026-04-29 | 2026-05-03 | 5 | G-02 | Planned
DEV-03 | Build | Build calendar sync and batch add capability | Development | 2026-04-30 | 2026-05-07 | 7 | DEV-02 | Planned
QA-03 | Quality | Conduct beta testing and defect triage | QA | 2026-05-08 | 2026-05-12 | 4 | DEV-03 | Planned
G-02 | Governance | Gate 3 beta readiness decision | PM | 2026-05-12 | 2026-05-12 | 1 | QA-03 | Planned
BA-04 | Analysis | Coordinate go-live readiness and deployment checklist | BA | 2026-05-13 | 2026-05-18 | 6 | G-03 | Planned
DEV-04 | Build | Implement conflict checks and production hardening | Development | 2026-05-13 | 2026-05-20 | 8 | G-03 | Planned
QA-04 | Quality | Execute regression testing and release validation | QA | 2026-05-19 | 2026-05-20 | 2 | DEV-04 | Planned
REL-01 | Release | Production deployment and handover | PM | 2026-05-21 | 2026-05-22 | 2 | QA-04 | Planned
Go-live | Governance | Monitor | BA | 2026-05-25 | 2026-06-19 | 26 | REL-01 | Planned
MON-01 | Monitoring | Review KPI trends, churn signals, and VOC feedback | BA | 2026-05-25 | 2026-06-19 | 26 | REL-01 | Planned